## Research Design
Research Design - PFR

## Design Think
DESIGN THINKING FLOW CHART - PFR

## ROAM
ROAM Analysis - PFR
ROAM Catogory | Issue | Actions Taken / Action Plan | ROAM Designation
Issue 1 | Partial facial data results in lower-than-expected match accuracy (e.g., masks, occlusions, angles). | • Conducted accuracy benchmarking using occlusion datasets. • Implemented hybrid feature-extraction techniques to improve recognition robustness. • Adjusted thresholds to reduce false positives. | Mitigated
Issue 2 | Bias in training data may cause reduced performance for specific demographic groups when only partial features are visible. | • Initiated dataset audit and diversity scoring. • Added supplemental training data focusing on underrepresented groups. • Scheduled fairness testing into QA cycle. | Owned
Issue 3 | Integration of different team members’ work (data prep, modelling, evaluation, ethics) | Create a shared project plan with internal milestones, use version control, and schedule at least one full “integration day” before final submission. | Owned
Issue 4 | Ethical and privacy concerns (misidentification, bias, misuse) may be underdeveloped in the final report. | Assign one team member to lead the ethics section, review current guidelines on responsible use of facial recognition, and include clear discussion of risks and safeguards. | Owned
Issue 5 | Real-time recognition performance drops on lower-end devices. | • Optimized model size with quantization and pruning. • Introduced device-adaptive model selection. • Added edge-processing fallback options. | Mitigated
Issue 6 | Scope creep: trying to build a full production-style system (web app, full pipeline) instead of a focused research prototype. | Agree a clear project scope with your lecturer; prioritize research questions and core experiments; treat deployment/web app discussion as conceptual rather than full implementation. | Accepted
Issue 7 | Confusion over roles and responsibilities among the four team members. | Clearly assign ownership for literature review, data and experiments, applications/architecture, and ethics; review responsibilities in weekly meetings. | Resolved
Issue 8 | Some experimental ideas (e.g., advanced architectures or quantum methods) may not be feasible in the available time. | Keep these as “stretch goals” and document them in future work rather than relying on them for core results. | Accepted
ROAM
R - Resolved
O - Owned
A - Accepted
M - Mitigated

## Status Report
Status Report - PFR
Date: 02nd December 2025
Summary |  |  |  | Overall Status (RAG)
The team has agreed project scope, divided roles, and started literature review and initial data exploration for partial facial recognition with occlusions. In the next stages we are going to plan our model End-to-End pipeline and Start to clean the dataset and then image processing while mitigating the risk and issues that will be occured. |  |  |  | Amber
Completed Milestones & Tasks
Tasks/ Milestones | Date | Status | Owner | Comments
Assign the Team Roles and Devide the responsibilities | 21st Oct | Completed | Project Manager | As per the first step of the Project decide the team roles and assign them after a meeting with all team members
Project Initiation | 20th Nov | Completed | Documentation Specialist | As stages we have presented our documents and got the comments to improve those.
Research design | 28th Nov | Completed | Project Manager | According to research workload we have devide into 4 stages and gave them to the Team members
On-going
Tasks/ Milestones | Date | Status | Owner | Comments
Researching (all team members as devided) | Present | On-going | All team | After assigng research catogories each of the team members are sharing their findings in the stand-up-meetings
Documentation | Present | On-going | Documentation Specialist | In the weekly meetings we all discuss and Documentation Specialist brings the documents as the project progress ahead.
Upcoming Milestones / Tasks
Tasks/ Milestones | Date | Status | Owner | Comments
Creating the End-to-End Pipeline | 20th Dec | Upcoming | Project Manager | After having findings from the research start to code the key factors and create the Pipeline
Data selection & Image Processing | 22nd Dec | Upcoming | ML Engineer | According to the Pipeline start the first step as slect the dataset along with the finding from the research and start the image processing(Face embeddings)
Top Risks & Issues
Issue | Impact | Action |  | Owner
Integration of the team members for the Scope | Fail to meet the deadlines of each tasks | Gather a meeting and speed up the process, Borrow some dates from the low prioratised Tasks |  | Project Manager
Documentation is not happening properly | Fail to update the stakeholders on time in the meetings | Ask Documentation Specialist to report the progress of the documents in the standup meetings to PM |  | Documentation Specialist
Dataset may not contain enough partial or occluded face images, which leading to poor real-world performance. | Low accuracy wil be occurred & need to be having lots of backpropagation | Research more about the Dataset and see whether we can map other datasets also |  | ML Engineer & Project Manager